## Drawing Log
Project Name: GSC Juniper RBP Phase II
OUTGOING DRAWING LOG SHEET
Sl. No. | Sheet No. | Drawing Title | Sent for Approval |  | Sent for Fabrication |  |  |  | Remarks | Sequence/ Area
|  |  | Rev A | Rev B | Rev 0 | Rev 1 | Rev 2 | Rev 3
DRAWINGS
1 | 1AL1 | LINTEL ANGLE |  |  | 11-04-2025 |  |  |  | For Fabrication
2 | 1AL2 | LINTEL ANGLE |  |  | 11-04-2025 |  |  |  | For Fabrication
3 | 1AL3 | LINTEL ANGLE |  |  | 11-04-2025 |  |  |  | For Fabrication
4 | 1AL4 | LINTEL ANGLE |  |  | 11-04-2025 |  |  |  | For Fabrication
5 | 1AL5 | LINTEL ANGLE |  |  | 11-04-2025 |  |  |  | For Fabrication
6 | 1AL6 | LINTEL ANGLE |  |  | 11-04-2025 |  |  |  | For Fabrication
7 | 1AL7 | ANGLE |  |  | 11-04-2025 |  |  |  | For Fabrication
8 | 1AL8 | ANGLE |  |  | 11-04-2025 |  |  |  | For Fabrication
9 | 1AL9 | LINTEL ANGLE |  |  | 11-04-2025 |  |  |  | For Fabrication
10 | 1AL10 | LINTEL ANGLE |  |  | 11-04-2025 |  |  |  | For Fabrication
11 | 1AL11 | ANGLE |  |  | 11-04-2025 |  |  |  | For Fabrication
12 | 1AL12 | ANGLE |  |  | 11-04-2025 |  |  |  | For Fabrication
13 | 1AL13 | ANGLE |  |  | 11-04-2025 |  |  |  | For Fabrication
14 | 1AL14 | ANGLE |  |  | 11-04-2025 |  |  |  | For Fabrication
15 | 1AL15 | ANGLE |  |  | 11-04-2025 |  |  |  | For Fabrication
16 | 1AL16 | ANGLE |  |  | 11-04-2025 |  |  |  | For Fabrication
17 | 1AL17 | ANGLE |  |  | 11-04-2025 |  |  |  | For Fabrication
18 | 1AL18 | ANGLE |  |  | 11-04-2025 |  |  |  | For Fabrication
19 | 1AL19 | ANGLE |  |  | 11-04-2025 |  |  |  | For Fabrication
20 | 1AL20 | ANGLE |  |  | 11-04-2025 |  |  |  | For Fabrication
21 | 1AL21 | ANGLE |  |  | 11-04-2025 |  |  |  | For Fabrication
22 | 1AL22 | ANGLE |  |  | 11-04-2025 |  |  |  | For Fabrication
23 | 1AL23 | ANGLE |  |  | 11-04-2025 |  |  |  | For Fabrication
24 | 1AL24 | ANGLE |  |  | 11-04-2025 |  |  |  | For Fabrication
25 | 1AL25 | ANGLE |  |  | 11-04-2025 |  |  |  | For Fabrication
26 | 1B1 | BEAM |  |  | 11-04-2025 |  |  |  | For Fabrication
27 | 1B2 | BEAM |  |  | 11-04-2025 |  |  |  | For Fabrication
28 | 1B3 | BEAM |  |  | 11-04-2025 |  |  |  | For Fabrication
29 | 1B4 | BEAM |  |  | 11-04-2025 |  |  |  | For Fabrication
30 | 1B5 | BEAM |  |  | 11-04-2025 |  |  |  | For Fabrication
31 | 1B6 | HSS GIRT |  |  | 11-04-2025 |  |  |  | For Fabrication
32 | 1B7 | HSS GIRT |  |  | 11-04-2025 |  |  |  | For Fabrication
33 | 1B8 | HSS GIRT |  |  | 11-04-2025 |  |  |  | For Fabrication
34 | 1B9 | HSS GIRT |  |  | 11-04-2025 |  |  |  | For Fabrication
35 | 1B10 | HSS GIRT |  |  | 11-04-2025 |  |  |  | For Fabrication
36 | 1B11 | HSS GIRT |  |  | 11-04-2025 |  |  |  | For Fabrication
37 | 1B12 | HSS GIRT |  |  | 11-04-2025 |  |  |  | For Fabrication
38 | 1B13 | HSS GIRT |  |  | 11-04-2025 |  |  |  | For Fabrication
39 | 1B14 | HSS GIRT |  |  | 11-04-2025 |  |  |  | For Fabrication
40 | 1B15 | HSS GIRT |  |  | 11-04-2025 |  |  |  | For Fabrication
41 | 1B16 | HSS GIRTS |  |  | 11-04-2025 |  |  |  | For Fabrication
42 | 1B17 | HSS GIRT |  |  | 11-04-2025 |  |  |  | For Fabrication
43 | 1B18 | HSS GIRT |  |  | 11-04-2025 |  |  |  | For Fabrication
44 | 1B19 | HSS GIRT |  |  | 11-04-2025 |  |  |  | For Fabrication
45 | 1B20 | HSS GIRTS |  |  | 11-04-2025 |  |  |  | For Fabrication
46 | 1B21 | HSS GIRT |  |  | 11-04-2025 |  |  |  | For Fabrication
47 | 1B22 | HSS GIRT |  |  | 11-04-2025 |  |  |  | For Fabrication
48 | 1B23 | HSS GIRT |  |  | 11-04-2025 |  |  |  | For Fabrication
49 | 1B24 | HSS GIRT |  |  | 11-04-2025 |  |  |  | For Fabrication
50 | 1B25 | HSS GIRT |  |  | 11-04-2025 |  |  |  | For Fabrication
51 | 1B26 | HSS GIRT |  |  | 11-04-2025 |  |  |  | For Fabrication
52 | 1B27 | HSS GIRT |  |  | 11-04-2025 |  |  |  | For Fabrication
53 | 1B28 | HSS GIRTS |  |  | 11-04-2025 |  |  |  | For Fabrication
54 | 1B29 | HSS GIRT |  |  | 11-04-2025 |  |  |  | For Fabrication
55 | 1B30 | HSS GIRT |  |  | 11-04-2025 |  |  |  | For Fabrication
56 | 1B31 | HSS GIRT |  |  | 11-04-2025 |  |  |  | For Fabrication
57 | 1B32 | HSS GIRT |  |  | 11-04-2025 |  |  |  | For Fabrication
58 | 1B33 | HSS GIRT |  |  | 11-04-2025 |  |  |  | For Fabrication
59 | 1B34 | HSS GIRT |  |  | 11-04-2025 |  |  |  | For Fabrication
60 | 1B35 | HSS GIRT |  |  | 11-04-2025 |  |  |  | For Fabrication
61 | 1B36 | HSS GIRT |  |  | 11-04-2025 |  |  |  | For Fabrication
62 | 1B37 | HSS GIRT |  |  | 11-04-2025 |  |  |  | For Fabrication
63 | 1B38 | HSS GIRT |  |  | 11-04-2025 |  |  |  | For Fabrication
64 | 1B39 | HSS GIRT |  |  | 11-04-2025 |  |  |  | For Fabrication
65 | 1B40 | HSS GIRT |  |  | 11-04-2025 |  |  |  | For Fabrication
66 | 1B41 | HSS GIRT |  |  | 11-04-2025 |  |  |  | For Fabrication
67 | 1B42 | TOTAL REMARKS ADV MILL # |  |  | 11-04-2025 |  |  |  | For Fabrication
68 | 1B43 | HSS GIRT |  |  | 11-04-2025 |  |  |  | For Fabrication
69 | 1B44 | BEAM |  |  | 11-04-2025 |  |  |  | For Fabrication
70 | 1B45 | BEAM |  |  | 11-04-2025 |  |  |  | For Fabrication
71 | 1B46 | BEAM |  |  | 11-04-2025 |  |  |  | For Fabrication
72 | 1B47 | BEAM |  |  | 11-04-2025 |  |  |  | For Fabrication
73 | 1B48 | BEAM |  |  | 11-04-2025 |  |  |  | For Fabrication
74 | 1B49 | BEAM |  |  | 11-04-2025 |  |  |  | For Fabrication
75 | 1B50 | HSS GIRT |  |  | 11-04-2025 |  |  |  | For Fabrication
76 | 1C1 |  |  |  | 11-04-2025 |  |  |  | For Fabrication
77 | 1C2 | TOTAL REMARKS ADV MILL # |  |  | 11-04-2025 |  |  |  | For Fabrication
78 | 1C3 |  |  |  | 11-04-2025 |  |  |  | For Fabrication
79 | 1C4 | COLUMN |  |  | 11-04-2025 |  |  |  | For Fabrication
80 | 1C5 | COLUMN | [6 empty] | For Fabrication
81 | 1C6 | COLUMN |  |  | 11-04-2025 |  |  |  | For Fabrication
82 | 1C7 | COLUMN |  |  | 11-04-2025 |  |  |  | For Fabrication
83 | 1C8 | COLUMN |  |  | 11-04-2025 |  |  |  | For Fabrication
84 | 1C9 | COLUMN |  |  | 11-04-2025 |  |  |  | For Fabrication
85 | 1C10 | COLUMNS |  |  | 11-04-2025 |  |  |  | For Fabrication
86 | 1C11 | COLUMN |  |  | 11-04-2025 |  |  |  | For Fabrication
87 | 1C12 | COLUMN |  |  | 11-04-2025 |  |  |  | For Fabrication
88 | 1C13 | COLUMN |  |  | 11-04-2025 |  |  |  | For Fabrication
89 | 1C14 | COLUMNS |  |  | 11-04-2025 |  |  |  | For Fabrication
90 | 1C15 |  |  |  | 11-04-2025 |  |  |  | For Fabrication
91 | 1C16 | COLUMN |  |  | 11-04-2025 |  |  |  | For Fabrication
92 | 1C17 | TOTAL REMARKS ADV MILL # |  |  | 11-04-2025 |  |  |  | For Fabrication
93 | 1C18 |  |  |  | 11-04-2025 |  |  |  | For Fabrication
94 | 1C19 | TOTAL REMARKS ADV MILL # |  |  | 11-04-2025 |  |  |  | For Fabrication
95 | 1C20 |  |  |  | 11-04-2025 |  |  |  | For Fabrication
96 | 1C21 | TOTAL REMARKS ADV MILL # |  |  | 11-04-2025 |  |  |  | For Fabrication
97 | 1C22 | SURFACE PREP. |  |  | 11-04-2025 |  |  |  | For Fabrication
98 | 1PL1 |  |  |  | 11-04-2025 |  |  |  | For Fabrication
99 | 1PL2 |  |  |  | 11-04-2025 |  |  |  | For Fabrication
100 | 1PL3 |  |  |  | 11-04-2025 |  |  |  | For Fabrication
101 | 1PL4 |  |  |  | 11-04-2025 |  |  |  | For Fabrication
102 | 1PL5 |  |  |  | 11-04-2025 |  |  |  | For Fabrication
103 | 1PL6 |  |  |  | 11-04-2025 |  |  |  | For Fabrication
104 | a14 - ANGLE - Rev 0 | ANGLE |  |  | 11-04-2025 |  |  |  | For Fabrication
105 | a15 - ANGLE - Rev 0 | ANGLE |  |  | 11-04-2025 |  |  |  | For Fabrication
106 | a21 - ANGLE - Rev 0 | ANGLE |  |  | 11-04-2025 |  |  |  | For Fabrication
107 | a56 - ANGLE - Rev 0 | ANGLE |  |  | 11-04-2025 |  |  |  | For Fabrication
108 | a57 - ANGLE - Rev 0 | ANGLE |  |  | 11-04-2025 |  |  |  | For Fabrication
109 | a59 - ANGLE - Rev 0 | ANGLE |  |  | 11-04-2025 |  |  |  | For Fabrication
110 | a60 - ANGLE - Rev 0 | ANGLE |  |  | 11-04-2025 |  |  |  | For Fabrication
111 | a75 - ANGLE - Rev 0 | ANGLE |  |  | 11-04-2025 |  |  |  | For Fabrication
112 | a101 - ANGLE - Rev 0 | ANGLE |  |  | 11-04-2025 |  |  |  | For Fabrication
113 | a105 - ANGLE - Rev 0 | ANGLE |  |  | 11-04-2025 |  |  |  | For Fabrication
114 | a106 - ANGLE - Rev 0 | ANGLE |  |  | 11-04-2025 |  |  |  | For Fabrication
115 | a107 - ANGLE - Rev 0 | ANGLE |  |  | 11-04-2025 |  |  |  | For Fabrication
116 | a108 - ANGLE - Rev 0 | ANGLE |  |  | 11-04-2025 |  |  |  | For Fabrication
117 | a109 - ANGLE - Rev 0 | ANGLE |  |  | 11-04-2025 |  |  |  | For Fabrication
118 | a110 - ANGLE - Rev 0 | ANGLE |  |  | 11-04-2025 |  |  |  | For Fabrication
119 | a111 - ANGLE - Rev 0 | ANGLE |  |  | 11-04-2025 |  |  |  | For Fabrication
120 | a112 - ANGLE - Rev 0 | ANGLE |  |  | 11-04-2025 |  |  |  | For Fabrication
121 | a113 - ANGLE - Rev 0 | ANGLE |  |  | 11-04-2025 |  |  |  | For Fabrication
122 | a114 - ANGLE - Rev 0 | ANGLE |  |  | 11-04-2025 |  |  |  | For Fabrication
123 | a115 - ANGLE - Rev 0 | ANGLE |  |  | 11-04-2025 |  |  |  | For Fabrication
124 | a116 - ANGLE - Rev 0 | ANGLE |  |  | 11-04-2025 |  |  |  | For Fabrication
125 | a117 - ANGLE - Rev 0 | ANGLE |  |  | 11-04-2025 |  |  |  | For Fabrication
126 | a118 - ANGLE - Rev 0 | ANGLE |  |  | 11-04-2025 |  |  |  | For Fabrication
127 | a120 - ANGLE - Rev 0 | ANGLE |  |  | 11-04-2025 |  |  |  | For Fabrication
128 | a145 - ANGLE - Rev 0 | ANGLE |  |  | 07-03-2025 |  |  |  | For Fabrication
129 | a146 - ANGLE - Rev 0 | ANGLE |  |  | 07-03-2025 |  |  |  | For Fabrication
130 | p9 - PLATE - Rev 0 | Tekla Structures |  |  | 11-04-2025 |  |  |  | For Fabrication
131 | p104 - PLATE - Rev 0 | Tekla Structures |  |  | 11-04-2025 |  |  |  | For Fabrication